NEIGHBORHOOD ISSUE LOGGER

Work Breakdown Structure (WBS)

10-Day Build Plan · Solo Developer · ~6–7 hrs/day

# Project Phasing Overview

| Phase | Focus | Days | Exit Criteria |
| --- | --- | --- | --- |
| 1. Setup | Environment, data model, auth skeleton | Day 1 | User can register / log in; DB connected |
| 2. Core Backend | Report CRUD, location grouping, upvotes/comments | Days 2–4 | All API endpoints tested via Postman |
| 3. Core Frontend | Report form, browse/list view, report detail page | Days 5–7 | User can create, view, and interact with reports end-to-end |
| 4. Pattern Detection | Aggregation pipeline, hotspot flag, per-address view | Day 8 | Address page shows live stats + hotspot flag |
| 5. Polish | Map view, filters, styling pass, seed data | Day 9 | App looks demo-ready, not a wireframe |
| 6. Ship | Deploy, README, demo script, final QA | Day 10 | Live URL + polished repo + 2-min demo rehearsed |

DAY 1 — Environment Setup & Data Model

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 1.1 | Initialize repo, Node/Express project structure, install core packages (express, mongoose, dotenv, bcrypt, jsonwebtoken) | 1.0 | Running Express server (“Hello World” route) |
| 1.2 | Create MongoDB Atlas cluster, connect via mongoose, set up .env config | 1.0 | DB connection confirmed in console log |
| 1.3 | Define Mongoose schemas: User, Report (with embedded comments/upvotes) | 1.5 | schemas/ folder with User.js, Report.js |
| 1.4 | Build auth routes: POST /register, POST /login (JWT issuance), auth middleware | 2.0 | Register/login working via Postman |
| 1.5 | Set up basic project folder structure for frontend (public/, views or separate client folder) | 0.5 | Folder scaffold committed to repo |

DAY 2 — Report CRUD (Backend)

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 2.1 | POST /reports — create report (title, description, category, address, lat/lng, occurredAt) | 1.5 | New reports saved to DB, linked to reportedBy |
| 2.2 | GET /reports — list all reports with query filters (category, date range, status) | 1.5 | Filterable list endpoint tested |
| 2.3 | GET /reports/:id — fetch single report with comments populated | 1.0 | Single report detail endpoint working |
| 2.4 | PATCH /reports/:id/status — update status (open/acknowledged/resolved) | 1.0 | Status transitions tested via Postman |
| 2.5 | Input validation (required fields, category enum) and error handling middleware | 1.5 | Bad requests return clean 400 errors, not stack traces |

DAY 3 — Location Grouping, Upvotes & Comments (Backend)

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 3.1 | Address normalization logic (lowercase, trim, strip punctuation) so “Same here” matches work reliably | 1.5 | normalizeAddress() util with unit-tested edge cases |
| 3.2 | POST /reports/:id/upvote — toggle upvote, prevent duplicate votes per user | 1.5 | Upvote count updates correctly, no double-counting |
| 3.3 | POST /reports/:id/comments — add comment; GET returns comments with report | 1.5 | Comment thread stored and retrievable |
| 3.4 | GET /addresses/:address/reports — all reports at a normalized address | 1.5 | Grouped report list by address confirmed |
| 3.5 | Photo upload integration (Cloudinary) — upload endpoint + store returned URL on report | 1.5 | Image uploads successfully attach to a report |

DAY 4 — Pattern Detection Aggregation (Backend)

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 4.1 | MongoDB aggregation pipeline: group reports by normalized address, count total + last-30-days count | 2.0 | Aggregation query returns correct per-address stats |
| 4.2 | GET /addresses/:address/stats — returns total reports, 30-day count, category breakdown, hotspot boolean (threshold-based) | 1.5 | Stats endpoint tested with seed data |
| 4.3 | Seed script: generate realistic demo data (multiple users, addresses, timestamps spanning 60 days) | 1.5 | seed.js populates DB with a believable dataset |
| 4.4 | Write/refine unit tests or manual Postman collection covering all endpoints built so far | 1.0 | Postman collection exported and saved to repo |
| 4.5 | Backend checkpoint: full API walkthrough, fix any bugs found | 1.0 | All endpoints verified working end-to-end |

DAY 5 — Frontend Foundation & Report Form

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 5.1 | Build base HTML layout, shared CSS (nav, containers, typography, color system) | 1.5 | Consistent page shell across all views |
| 5.2 | Register/login pages, JS fetch calls to auth API, store JWT (localStorage) | 2.0 | User can register and log in from the UI |
| 5.3 | “New Report” form: title, description, category dropdown, date/time picker, address field | 1.5 | Form submits and creates a report via API |
| 5.4 | Integrate Leaflet.js map picker for pinning report location | 1.5 | Clicking map sets lat/lng on the form |

DAY 6 — Browse & List View

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 6.1 | Reports list page: fetch and render all reports as cards (title, category badge, address, date) | 2.0 | List view populated from live API data |
| 6.2 | Category and date-range filter controls wired to GET /reports query params | 1.5 | Filtering updates the list without a full page reload |
| 6.3 | Status badge styling (Open / Acknowledged / Resolved) with distinct colors | 1.0 | Status is visually scannable at a glance |
| 6.4 | Empty-state and loading-state handling for the list view | 1.0 | No blank/broken screen while data loads or when empty |
| 6.5 | Basic responsive pass (mobile breakpoint for list and nav) | 0.5 | List usable on a narrow viewport |

DAY 7 — Report Detail, Upvotes & Comments (Frontend)

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 7.1 | Report detail page: full description, photo, map pin, metadata | 1.5 | Clicking a card opens a complete detail view |
| 7.2 | “Same here” upvote button wired to API, optimistic UI update | 1.5 | Upvote count updates instantly on click |
| 7.3 | Comment thread UI: list existing comments, add-comment form | 1.5 | New comments appear without a page reload |
| 7.4 | Photo upload UI on the report form (file input → Cloudinary → preview) | 1.5 | Selected photo previews and uploads correctly |
| 7.5 | End-to-end smoke test: create → view → upvote → comment, as two different demo users | 1.0 | Full user loop works without console errors |

DAY 8 — Pattern Detection View (Frontend)

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 8.1 | Per-address page: fetch /addresses/:address/stats and render summary numbers | 1.5 | Address page shows total + 30-day counts live |
| 8.2 | Chart.js integration: category breakdown (bar/pie) and report frequency over time (line) | 2.0 | Two working charts driven by real aggregation data |
| 8.3 | Hotspot flag UI: visually distinct banner/badge when threshold is crossed | 1.0 | Hotspot addresses are unmistakable at a glance |
| 8.4 | Link from report cards/list → corresponding address pattern page | 1.0 | Navigation between list and address view feels connected |
| 8.5 | Map view: plot all reports as pins, color-coded by category or hotspot status | 1.5 | Neighborhood map view renders live pins |

DAY 9 — Polish, Styling & Seed Data

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 9.1 | Full visual design pass: consistent spacing, color system, button/form states, icons | 2.0 | App looks like a designed product, not scaffolding |
| 9.2 | Populate final seed dataset with a compelling demo narrative (one address clearly a hotspot) | 1.0 | Demo data tells the pattern-detection story convincingly |
| 9.3 | Cross-browser/device check; fix any layout breakage | 1.0 | App looks correct on Chrome + mobile width |
| 9.4 | Error-state polish (failed uploads, network errors, invalid form input) | 1.0 | No raw error text or broken states visible to a user |
| 9.5 | Code cleanup: remove console.logs, dead code, consistent formatting | 1.0 | Repo is presentable if an interviewer opens it |

DAY 10 — Deployment & Demo Readiness

| Task ID | Task | Est. Hrs | Deliverable |
| --- | --- | --- | --- |
| 10.1 | Deploy backend (Render/Railway) and connect to MongoDB Atlas production settings | 1.5 | Live backend URL responding correctly |
| 10.2 | Deploy/serve frontend (same host or Netlify/Vercel), wire to live backend URL | 1.5 | Fully working live app at a public URL |
| 10.3 | Write README: problem statement, features, tech stack, setup instructions, screenshots | 1.5 | README reads like a real product case study |
| 10.4 | Prepare and rehearse the 2-minute demo script (see Success Criteria in Business Scope Brief) | 1.0 | Demo flows smoothly without hesitation |
| 10.5 | Final QA pass on the live deployed version (not just localhost) | 1.0 | No bugs found in the production environment |

# Effort Summary

| Phase | Days | Approx. Hours |
| --- | --- | --- |
| Setup | Day 1 | 6.0 |
| Core Backend | Days 2–4 | 19.5 |
| Core Frontend | Days 5–7 | 19.5 |
| Pattern Detection | Day 8 | 7.0 |
| Polish | Day 9 | 6.0 |
| Ship | Day 10 | 6.5 |
| Total | 10 Days | ~64.5 hrs |

Note: ~6.5 hrs/day average leaves buffer for a beginner's slower debugging pace. If a task overruns, cut from Day 9 polish or Stretch Features first — never from the Day 4 aggregation pipeline or Day 8 pattern view, since those are what differentiate this project on a portfolio.